## Sheet1
TEAM JAVADIATORS - Alvaro, Aleix, Josep, Jordi, Jorge
| Date | Time | Place | Participants | Notes
First meeting | 2018-01-01 | 19:00 -20:00 | Skype meeting | Whole team | • Work analisis. Decided to go to second call. Action points • Whole team: Enjoy the exams, see you in 22th
Second meeting | 2018-01-22 | 18:00 - 21:00 | Skype meeting | Whole team | • First analisys of the full code. • Decided to let 2 days for everyone to read it and understand the behavior and how do they work Action points • Everyone should analyse the code.
Third meeting | 2018-01-25 | 19:00 - 21:00 | Skype meeting | Whole team | • Divide work - Jordi & Josep: Digger and DiggerCoordinator. - Alvaro & Jorge: Prospector and Prospector Coordinator. - Aleix: System agent. Action points • Start working on each group part.
Fourth meeting | 2018-01-26 | 18:00 - 21:00 | Skype meeting | Whole team | • Merge the work from each group and work into the coordinator agent to do it. Action points • Next two days work together and try to have the code finished by Sunday night.
Fifth meeting | 2018-01-28 | 23:00 - 00:00 | Skype meeting | Whole team | • Analyze bugs and errors of the code and start fixing them. Action points • The found errors have to be fixed.
Sixth meeting | 2018-01-30 | 23:00 - 00:00 | Skype meeting | Whole team | • Analize possible improvements and set the report template. Action points • Make the improvements, write the report, and make the PPT.
Seventh meeting | 2018-02-01 | 00:00 - 01:00 | Skype meeting | Whole team | • Delivery.